# Appendix A-2: Milestone Policy

Design project sponsors must include, at minimum, a completed project concept as part of their application and work to advance their project through 30-percent design, 60-percent design or final design.

Construction project sponsors must include 30-percent design plans with their TAP application. The 30-percent plans are the starting point of further project development. Plans for the approved projects should not drop below this 30-percent stage after the TAP Selection Committee has approved them. Projects requiring a restart of the design process should be withdrawn and resubmitted when 30-percent design plans are again achieved.

Construction project sponsors expected to bring their projects to the 60-percent design stage within one year of the kickoff meeting must advertise construction projects within two years of the project kickoff meeting. The kickoff meeting is held for all approved projects within two months of the date on which the MDOT SHA Administrator signs the approval letter. Communication to MDOT SHA, through monthly progress, from project sponsors are expected to ensure project progress is timely. If project does not meet the Milestone Policy requirement, MDOT SHA will notify project sponsors to address concerns before sharing update with TAP Selection Committee, who can make final approval to withdraw the funds for each project. At that point, MDOT SHA will notify the project sponsors that funding is being withdrawn.

Design Concepts for Project Applications

If submitting a project concept as part of the application, a complete design concept must include:

- Plan level drawings demonstrating alignment of project

- Limits of disturbance shown on drawing

- Right-of-way impacts based on the limits of disturbance

- Demonstrate direct contact with all affected property owners

- Include planning level rough costs and material needs

Project sponsors are encouraged to utilize MPOs’ unified planning work programs, the TLC grant program, and the MDOT Bikeways program when developing these items.

30 Percent Status Definition

The following table provides a summary of general items that make up 30-percent plans for eligible streams, wetlands, trails, buildings, and bridge (structures) projects. This summary is not inclusive of all activities that may be needed, and the absence of an item on the list does not mean that it is not needed or required. Planning, development, design, and execution of projects will vary, as will project needs and the state and federal rules and regulations that apply.

| Stream Projects (30-Percent) |  |
| --- | --- |
| - Title Sheet | - Bank Stabilization |
| - Location Map | - Detail Sheet(s) |
| - Stream Use and Closure Dates | - Typical Section |
| - Legend | - Typical Riffle |
| - Scale | - Typical Pool |
| - Grading Plan | - Bank Width/Depth |
| - Existing and Proposed Topography | - Flood-prone Area |
| - Construction Access | - Grading Limits |
| - Preliminary Sequence of Construction | - Profile |
| - Baseline of Construction | - Planting Plan |
| - Land Cover (tree line, floodplain limit, existing features) | - Planting Zone |
| - In-stream Structure Locations | - Plant List |
| - Property Needs Identified |  |
| Wetland Projects (30-Percent) |  |
| - Title Sheet | - Construction Access |
| - Location Map | - Preliminary Sequence of Construction |
| - Legend | - Baseline of Construction |
| - Scale | - Land Cover (tree line, floodplain limit, existing features) |
| - Grading Plan | - Planting Plan |
| - Existing and Proposed Topography | - Planting Zone |
| - Wetland Limit by Type | - Plant List |
| - Groundwater well/piezometer location | - Property Needs Identified |

| Trail Projects (30-Percent) |  |
| --- | --- |
| - Title Sheet with location map, legend for existing and proposed items, including shading, scale (largest 100’:1”), north arrow | - Design Plan Sheets - Survey line w/bench marks/datum used to locate existing facilities and topography for the project’s design - A feasible horizontal and vertical alignment of the proposed trail, spur trails, and destination/connector trails - Geometric values and stationing, on a table and on/near the alignment - Existing topography - Roadway traffic direction arrow - Identify existing facilities, buildings - Floodplain, streams, ditches, storm drain systems, etc. - Utilities Location/Designation (horizontal location) - Existing and Proposed Right-of-Way Lines - Construction Access Location Identified - Limits of Toe/Top of Fill/Cut - Typical Sections (with existing and proposed surfaces) with applicable station limits - Grade and Cross Slope - Preliminary Pavement Section - Cut and Fill Slopes - Limit of Work - Proposed Stormwater Management Location and Devices - Cross Section Sheets at Minimum 200’ intervals - Detailed drawings of elements proposed such as non-SHA Book of Standards and C&G inlets, fencing, gates, ADA compliance elements, short retaining walls, light structures (bridges, box culverts, and retaining walls), buildings, etc. - Projects that propose boardwalks (elevated walkways), bridges, and retaining walls will include information noted on applicable status lists |
| - All necessary dimensions and stations to identify and locate existing features, including topography and underground utilities |  |
| - Size and location of all major improvements, including trail alignments, trailheads, etc. |  |
| - If known, location of proposed amenities such as fences, railings, barriers, lighting, landscaping, sidewalks, entrances, etc. |  |
| - Proposed Edge of Pavement |  |
| - Existing and Proposed Right-of-Way |  |
| - Match Lines |  |
| - Any Needed Demolition Identified |  |
| - Property Needs Identified |  |
| - Major quantity estimate with specific line items for known elements, such as light fixtures, traffic barriers, structures, building, utility relocations, etc. |  |

| Building Projects (30-Percent) |  |
| --- | --- |
| - Location Map | - Existing and preliminary utility locations, including plumbing, HVAC, electrical, and sewer |
| - Legend | - ADA Accommodations |
| - Scale | - Property Needs Identified |
| - Floor Plans | - Parking Facilities |
| - Property Lines | - Edge of Pavement |
| - All Necessary Dimensions | - Drainage Facilities |
| - Existing and Proposed Topography and Adjoining Structures | - Signage Locations |
| - Existing and Proposed Features | - Any needed demolition identified |
| - Proposed Improvements, including the function of each room | - Limits of Grading |
| - If known, location of proposed amenities, including landscaping, sidewalks, benches, etc. | - Major Quantities Estimate |
| Bridge Projects (30-Percent) |  |
| - Title Sheet | - North Arrow |
| - Location Map | - All existing dimensions and stations |
| - Legend | - Existing features, including topography and underground utilities |
| - Scale | - Type, Size, and Line of Structure |
| - Typical Sections | - Soil boring locations and logs included in plans |
| - Station Limits | - Bridge Thickness |
| - Grading and Cross Slope | - Elevation |
| - Type, Class and Thickness of Pavement and Base | - Top of Fill and Slope of Fill |
| - Abutments | - Limit of Work |
| - Existing and Proposed Under-Clearance | - Match Lines |
| - Property Needs Identified | - Any needed demolition identified |
| - Plan Sheets |  |

60 Percent Status Definition

The following table provides a summary of general items that make up 60-percent plans for eligible streams, wetlands, trails, buildings, and bridge (structures) projects. This summary is not inclusive of all activities that may be needed, and the absence of an item on the list does not mean that it is not needed or required. Design and execution of projects will vary, as will project needs and the state and federal rules and regulations that apply.

It is expected that these elements build upon the 30-percent design plans and maintain the same scope and limits of work approved for TAP funding submitted in the application.

| Stream Projects (60-Percent) |  |
| --- | --- |
| In addition to elements noted in the 30-percent status table: |  |
| - Completed Title Sheet | - Detailed plans with property lines, utilities, and all design items |
| - Cross Sections with Existing and Proposed Grades | - Stream Diversion Details |
| - NEPA Completed | - Structure Details – if included |
| - Planting Plans/Schedule/Species Identified | - Erosion and Sediment Control Plans Complete |
| - Property Acquisition Underway or Complete | - Refined Construction Estimate |
| - Profile Sheets |  |
| Wetland Projects (60-Percent) |  |
| In addition to elements noted in the 30-percent status table: |  |
| - Completed Title Sheet | - Planting Plans/Schedule/Species Identified |
| - Cross Sections with Existing and Proposed Grades | - Detailed plans with property lines, utilities, and all design items |
| - NEPA Completed | - Erosion and Sediment Control Plans Complete |
| - Property Acquisition Underway or Complete | - Refined Construction Estimate |

| Trail Projects (60-Percent) |  |
| --- | --- |
| In addition to elements noted in the 30-percent status table: |  |
| - Erosion and sediment control design plans and preliminary E&S permit approval | - Property Acquisition Underway or Complete |
| - Location and design of stormwater management facilities, closed storm drainage system, culverts and preliminary permit approval | - Location of Proposed Staging Area |
| - Cross sections at minimum 50’ interval | - Typical sections with proposed elements, such as signage, traffic barrier, fencing, structures, etc. |
| - Property lines, utilities, all design items, baseline, roadways | - Plan sheet with connecting design details to adjoining/intersection properties’ entrances, roads, trails, and spur that demonstrate compliance with MDOT SHA ADA guidelines |
| - NEPA completed and submitted to FHWA | - MDOT SHA concurrence on ADA compliance |
| - Trail projects that propose structures (bridges, box culverts, retaining walls, elevated walkways) have obtained MDOT SHA Office of Structures concurrence and TS&L, Foundation Design, Soil Boring Report, and Scour Analysis Report | - Vertical alignment with underground utilities and locations of structures |
| - Line item construction cost estimate with breakdown of lump sum items | - Proposed landscaping details and location |
| - Erosion and sediment control plans complete | - Detail sheets demonstrating all proposed elements noted on design plans, such as pedestrian and traffic lighting plans, structures, regulatory and informational signage, etc. |
| - Value Engineering complete – if required | - Refined Cost Estimate |
| Building projects (60-Percent) |  |
| In addition to elements noted in the 30-percent status table: |  |
| - Cross Sections | - Value Engineering complete – if required |
| - NEPA Completed | - Location and design of stormwater management facilities, closed storm drainage system, culverts, and preliminary permit approval |
| - Refined Cost Estimate | - MDOT SHA architect’s structural review completed and concurrence provided |
| - Detail plans with property lines, utilities, all design items, baseline, roadways | - Property acquisition underway or complete |
| - Erosion and sediment control design plans and preliminary erosion and sediment control permit approval |  |
| Bridge Projects (60-Percent) |  |
| In addition to elements noted in the 30-percent status table: |  |
| - Cross Sections | - Value Engineering complete – if required |
| - Additional Typical Sections | - MDOT SHA Office of Structures concurrence on TS&L, Foundation Design, Soil Boring Report, and Scour Analysis Report. Structural and Final Design concurrence needed with submittal for FHWA authorization and approval to advertise |
| - NEPA Completed | - Property acquisition underway or complete |
| - Erosion and sediment control plans complete | - Refined Construction Estimate |