# Appendix D-2: Design Project Process

☐ Begin project design after Notice to Proceed has been issued.

☐  Host kick-off meeting with consultants and review the TAP manual and Milestone Policy to understand design review points and design standards.

☐  Submit electronic 30-percent plans to TAP staff. Staff will distribute for discipline review.

☐ Access Permit: coordinate with MDOT SHA Access Management Division and District Liaison

☐ Address 30-percent plan comments

☐ Submit electronic 60-percent plans to TAP staff. Staff will distribute for discipline review.

☐ Access Permit: continue coordination

☐ Address 60-percent plan comments

☐ Obtain other MDOT SHA approvals and concurrences as identified by the TAP staff

☐ Obtain utility certification statement for all involved companies, even if no impacts are anticipated

☐ Submit electronic final design plans to TAP staff. Staff will distribute for discipline review.

☐ Access Permit: Obtain permit

☐ If advancing to construction:

☐ Assemble PS&E package (PS&E Checklist is available in Appendix C-5).

☐ Submit draft PS&E package.

☐ Host a Final Review Meeting before advertisement.

☐ Submit final, ready to advertise PS&E package, with approved Final Review Report to TAP staff with request for approval to advertise.