# Appendix D-3: Construction Project Process

☐ Prior to construction, contact and share relevant documents with MDOT SHA District Office

☐ Conduct a pre-construction meeting. Record and distribute meeting minutes.

☐ Confirm all relevant permits and preconstruction steps are satisfied

☐ Set up a project (field) office and ensure the field office maintains:

☐ a compliant record keeping system

☐ contract compliance

☐ DBE

☐ wage rates

☐ permits

☐ ROW documents

☐ Submit a project schedule (project sponsor to maintain, update, post as needed)

☐ Submit Traffic Control Manager information

☐ Approve subcontractors involved in the project construction

☐ Hold regular meetings with the contractor and prepare meeting minutes. Distribute minutes.

☐ Obtain Material Clearance, completing these four steps for all construction material prior to use:

☐ Submission (at least 30 days in advance of construction schedule) - Request meeting related to MMS if unfamiliar. Create MMS account with assistance from AME.

☐ Source Approval – Add SOS to MMS

☐ Testing – Follow processes and procedures outlined by OMT, MMS and related manuals

☐ Reporting – Obtain material acceptance and record all material tickets in the IDR.

☐ Begin submitting Monthly Clearance Report to OMT for review

☐ Begin construction and Inspector Daily Report

☐ If needed, follow the following steps for Change Orders

☐ Notify District Engineer (DE) and TA Program staff about possible change orders. Obtain concurrence from DE.

☐ Obtain written request of change order need from contractor

☐ Compile independent cost estimate, share with DE and compare to contractor’s estimate

☐ Prepare draft Change Order forms and submit to DE (copy to TA Program staff) for review

☐ Send final change orders to contractor for signature then to MDOT SHA for final approval. If approved, notify contractor and include with future contractor invoices.

☐ Final Inspection and Audit

☐ Prepare project punchlist

☐ Work with contractor to complete punchlist items

☐ Schedule and conduct final inspection in coordination with District Liaison and local jurisdiction

☐ Contact District Liaison to obtain checklist of records needed to enter contract finals

☐ Address audit discrepancies, if needed

☐ Notify TAP staff for concurrent before releasing retainage

☐ Request final material certification using form OOC 26 (Appendix D-10)

☐ Obtain partial or final acceptance and notify contractor