# Appendix D-5: Sample Monthly Progress Meeting Agenda and Minutes

# Sample Agenda for Monthly Meeting

| SM7965184R LEONARDTOWN STREETSCAPE June 16, 2009 at 10 a.m. At Field office conference room |  |  |
| --- | --- | --- |
| TIME | AGENDA ITEM | LEAD PERSON |
| 10:00-10:15 | Welcome, Introductions, Review Project Rating Form Results & Fill Out | Greta Hartman |
| 10:15-10:30 | Status of Project | Karen Grey |
| 10:30-11:45 | Review Current and New Issues |  |
|  | 4/08 #5 Status of Change Orders – Gas Tank | Robert Murphy |
|  | 5/08 #3 Slope Failure At Camp Calvert Rd. | Brandon Scott & Robert |
|  | 11/08 #1 Intersection Signal Turn-on update | Greta |
|  | 11/08 #2 Verizon Line on Fenwick St. @1-21 &1-22 CIP Status | Sean Johnson & Brandon |
|  | 2/09 #2 Redline Update | Sean |
|  | 3/09 #1 Brick Wall @ 300 +75 Centerline Washington St. | Sean, Linda, Karen & Greta |
|  | 5/09 #1 CMP at Courthouse Dr. Not shown on plans | Brandon, Greta & John |
| NEW ISSUES |  |  |
| 11:45-12:00 | Review Action Items and Person(s) Responsible | Greta |

Sample Monthly Meeting Minutes

List of Meeting Attendees

Results of Partnering Ratings

Document Progress Part of Meeting

Tracking Issues (Issues identified with a tracking number – month/year/issue i.e 4/08 #5 = April, 2008, 5th issue)

- 4/08 #5 and 8/08 #3 - Change Order Status-Meeting tomorrow 9-17-08@ 1:30 p.m. with Contractor and district to discuss change orders and schedule (ACR) within 1 week.

- 4/08 #7 - Survey Issues- D-5 survey crew took shots on Washington St. Rt. Centerline-Reviewed afterward and walked jobsite with OHD-awaiting new grades

- 5/08 #3 - Slope Failure-Headquarters emailed a possible solution to the district-still waiting to see if it will be an addition to the project or done thru maintenance or private sector. Will keep on agenda and in touch with Headquarters and address at a future date.

- 8/08 #2 - Sewer Line Conflict- I-47 to Camp Calvert Rd. have been purchased and manufactured. Headquarters left a rough draft/unauthorized copy with the contractor to review. Headquarters will expedite approval as soon as possible (within 2 weeks).

- 8/08 #5 - Raising Meters- Town of Leonardtown will supply material- Contractor will raise/adjust. 1own rep. mentioned updating the waterline on Fenwick St. to help withstand the vibrations from the construction work.

- 9/08 #1 - Curb at radius of Shadrick St. Fire dept. and Town requested depressed and/or 'Type 'C" mountable-would not meet A.D.A. spec.-Headquarters will take a look in the field. May be possible to shorten the radius to accommodate the fire trucks. (within 2 weeks)

(As issues are resolved they are deleted from the minutes.)

Next Meeting: Note date/time of next meeting

Things get done when you list:

- WHAT needs to occur,

- WHO is responsible or taking the lead, and

- WHEN it is expected to be done.